## Phases
Phase | Start Date | End Date | Description
Foundations | 2025-01-06 | 2025-01-26 | This phase focuses on setting up the foundational elements of the project, including data collection, annotation, and preliminary analysis.
Core Development | 2025-01-27 | 2025-02-16 | In this phase, we build the YOLO model, implement pipelines for data processing, and integrate detection and analysis capabilities.
Data Extraction & Trend Analysis | 2025-02-17 | 2025-03-08 | This phase emphasizes extracting insights from data and optimizing pipelines for performance and scalability.
Finalization & Deployment | 2025-03-09 | 2025-04-04 | The final phase involves testing, deployment preparation, production deployment, and delivering the final presentation with documentation.

## Roadmap
Roadmap (Jan 6–Feb 16, Weeks 1–6)
WIP
Completed
Road Block
Stopped
Week Number | Date Range | Task | Dependencies | Sub-Task Description | Detailed Description | Assigned Person | Phase | Status
1 | Jan 6–Jan 12 | Data Collection | None | Gather diverse chart samples from various sources | Search and collect charts (bar, line, pie) from open-source datasets, online repositories, etc. | Neel | Foundations
1 | Jan 6–Jan 12 | Data Collection | None | Organize and categorize the collected datasets | Categorize datasets based on chart type and relevance for training and validation. | Kedar | Foundations
1 | Jan 6–Jan 12 | Data Collection | None | Validate the quality of datasets | Check for missing data, resolution quality, and relevance for AI training. | Kartik | Foundations
1 | Jan 6–Jan 12 | Data Collection | None | Prepare dataset for annotation | Resize, crop, or clean chart images to make them suitable for annotation tasks. | Devi | Foundations
1 | Jan 6–Jan 12 | Checkpoint | Completion of all tasks for Week 1 | Weekly review of tasks, challenges, and learnings | Discuss progress, roadblocks, and lessons learned from the first week. | Team | Foundations
2 | Jan 13–Jan 19 | Data Annotation | Completion of Data Collection | Annotate charts with bounding boxes for key elements | Draw bounding boxes around legends, titles, axes, and data points using annotation tools. | Neel | Foundations
2 | Jan 13–Jan 19 | Data Annotation | Completion of Data Collection | Review and validate annotations | Cross-check and correct errors in bounding boxes to maintain high accuracy. | Kedar | Foundations
2 | Jan 13–Jan 19 | Data Annotation | Completion of Data Collection | Manage annotation files and formats | Organize annotated files in required formats (e.g., JSON, XML). | Kartik | Foundations
2 | Jan 13–Jan 19 | Data Annotation | Completion of Data Collection | Perform sample testing of annotated data | Verify annotations work seamlessly with Tesseract/YOLO inputs. | Devi | Foundations
2 | Jan 13–Jan 19 | Checkpoint | Completion of all annotation tasks | Weekly review of tasks, challenges, and learnings | Discuss task completion, tool functionality, and teamwork coordination. | Team | Foundations
3 | Jan 20–Jan 26 | Text Extraction | Completion of Data Annotation | Implement OCR pipeline using tools like Tesseract | Build a pipeline to extract textual elements from annotated chart areas (titles, legends, etc.). | Neel | Core Development
3 | Jan 20–Jan 26 | Text Extraction | Annotated datasets prepared | Test OCR on title and legend texts | Evaluate Tesseract’s performance on extracting text from sample charts. | Kedar | Core Development
3 | Jan 20–Jan 26 | Text Extraction | Annotated datasets validated | Validate extracted text against annotations | Compare OCR output with annotated data for accuracy. | Kartik | Core Development
3 | Jan 20–Jan 26 | Text Extraction | Annotated datasets processed | Perform additional OCR tuning | Modify OCR configurations (e.g., thresholding) for better accuracy. | Devi | Core Development
3 | Jan 20–Jan 26 | Checkpoint | Completion of all OCR-related subtasks | Weekly review of tasks, challenges, and learnings | Share OCR results, discuss errors, and plan re-tuning strategies. | Team | Core Development
4 | Jan 27–Feb 2 | YOLO Model | Annotated datasets processed | Set up YOLO for element detection | Configure YOLO framework and load pre-trained weights for chart element detection. | Neel | Core Development
4 | Jan 27–Feb 2 | YOLO Model | Annotated datasets validated | Train YOLO on annotated data | Train YOLO using the prepared and annotated datasets. | Kedar | Core Development
4 | Jan 27–Feb 2 | YOLO Model | Initial YOLO setup completed | Test YOLO on validation datasets | Evaluate YOLO’s ability to detect chart elements on unseen validation datasets. | Kartik | Core Development
4 | Jan 27–Feb 2 | YOLO Model | YOLO training started | Implement model tuning and re-training | Adjust YOLO’s hyperparameters and retrain to improve detection accuracy. | Devi | Core Development
4 | Jan 27–Feb 2 | Checkpoint | YOLO setup and testing completion | Weekly review of tasks, challenges, and learnings | Analyze YOLO’s outputs, review performance metrics, and finalize next steps. | Team | Core Development
5 | Feb 3–Feb 9 | Text Summarization | OCR results validated | Implement a summarization pipeline | Develop a script to generate concise text summaries for chart insights. | Neel | Data Extraction & Trend Analysis
5 | Feb 3–Feb 9 | Text Summarization | Text summarization pipeline set up | Validate summarization results | Cross-check summaries against extracted text for correctness and quality. | Kedar | Data Extraction & Trend Analysis
5 | Feb 3–Feb 9 | Text Summarization | OCR integrated with summarization script | Integrate summarization output with OCR pipeline | Combine OCR and summarization results into a single processing flow. | Kartik | Data Extraction & Trend Analysis
5 | Feb 3–Feb 9 | Text Summarization | Initial summaries generated | Review summarization performance metrics | Evaluate the readability and informativeness of the generated summaries. | Devi | Data Extraction & Trend Analysis
5 | Feb 3–Feb 9 | Checkpoint | Summarization tasks reviewed | Weekly review of tasks, challenges, and learnings | Discuss summarization flow and integrate team feedback. | Team | Data Extraction & Trend Analysis
6 | Feb 10–Feb 16 | Data Trend Analysis | Summarization pipeline finalized | Develop a trend analysis pipeline | Write scripts to analyze trends across summarized chart data. | Neel | Data Extraction & Trend Analysis
6 | Feb 10–Feb 16 | Data Trend Analysis | Summarization results validated | Visualize trends using Python libraries | Use Matplotlib/Seaborn to plot trends and insights from extracted data. | Kedar | Data Extraction & Trend Analysis
6 | Feb 10–Feb 16 | Data Trend Analysis | Summarization outputs generated | Automate trend reporting | Build a script to generate trend reports (PDF or HTML). | Kartik | Data Extraction & Trend Analysis
6 | Feb 10–Feb 16 | Data Trend Analysis | Initial trends identified | Validate trend analysis results | Compare trends with original charts to ensure reliability. | Devi | Data Extraction & Trend Analysis
6 | Feb 10–Feb 16 | Checkpoint | Initial trends reviewed | Weekly review of tasks, challenges, and learnings | Share analysis outputs and discuss report formats. | Team | Data Extraction & Trend Analysis